## DFSS Charter DMADV
<Company>
DFSS Project Charter
Program
Product
Category(BB/GB)
Name of Belt
Mater Black Belt (MBB)
Sponsor
Start Date
Business Opportunity
Short statement of the project delivearable
Project Deliverables and Goals | Performance
Reliability
Cost
Regulatory
Finiancials (NPV/Payback)
Market Segment(s)/Customer
Project Scope
Team Members
Schedule | Milestone | Planned Date | Actual Date
Start
Define
Measure
Analyze
Design and develop
Verify/Validate
Approvals | Sponsor | MBB | Finance

## DFSS Charter CDOV
<Company>
DFSS Project Charter
Program
Product
Category(BB/GB)
Name of Belt
Mater Black Belt (MBB)
Sponsor
Start Date
Business Opportunity
Short statement of the project deliverable
Project Deliverables and Goals | Performance
Reliability
Cost
Regulatory
Financials (NPV/Payback)
Market Segment(s)/Customer
Project Scope
Team Members
Schedule | Milestone | Planned Date | Actual Date
Start
Concept Phase Completed
Design Phase Completed
Optimize Phase Completed
Verify Phase Completed
Approvals | Sponsor | MBB | Finance

## DFSS Charter CDOV Example
<Company>
DFSS Project Charter
Program | Reliability Improvement
Product | M Series camshaft
Category(BB/GB) | BB
Name of Belt | XYZ
Mater Black Belt (MBB) | ABC
Sponsor | PQR
Start Date | 2015-01-20
Business Opportunity | B-10 life of camshafts is 14000 hours. This is lower than competition and needs improvement to improve customer confidence in the product.
Short statement of the project deliverable
Project Deliverables and Goals | Performance
| Reliability | Improve B10 life from 14000 to 25000 hours
Cost
Regulatory
Financials (NPV/Payback)
Market Segment(s)/Customer | Genset
Project Scope | M Series model only
Team Members | A, B, C, D
Schedule | Milestone | Planned Date | Actual Date
| Start | 2015-01-20
| Concept Phase Completed | 2015-02-15
| Design Phase Completed | 2015-04-15
| Optimize Phase Completed | 2016-06-15
| Verify Phase Completed | 2016-09-15
Approvals | Sponsor | MBB | Finance